## Structure
Flow of Bill from Sub Divison to Division to Head Quarter
SUB DIVISION |  | DIVISION |  | Head Quarter |  | MD(Final Authority)
3 Users | Clerk | 3 Users | SA | 3 Users | SA | 1 user
| JE |  | SUPTD |  | SUPTD
| SDO |  | XEN |  | CFA
In case of Devition bill sent to Engg. Dept. by Head Quarter |  |  |  | Engineering Department | SUPTD
|  |  |  | 3 Users | XEN PLANNING
CHIEF ENGINEER

## Projects
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | HUDCO funded Scheme - Construction of 95 Police Station Buildings | ',' | 1500000000 | ',' | 250000000 | ',' | 0 | ',' | 0 | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | Modernisation of State Police Forces Scheme for 2013-14 (State Share) | ',' |  | ',' |  | ',' |  | ',' |  | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | Modernisation of State Police Forces Scheme for 2014-15 (State Share) | ',' |  | ',' |  | ',' |  | ',' |  | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | Works to be executed with Rs. 17.71 crores (Rs. 10.34 crores of 13th finance Commission + 7.37 crores saving from 13th Finance Commission) | ',' |  | ',' |  | ',' |  | ',' |  | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | Works to executed out of Unexecuted funds of Modernisation of Police force Scheme and Savings from already executed works of Modernisation Scheme (4.16 Crores) | ',' |  | ',' |  | ',' |  | ',' |  | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | Execution of works under Interest Accrued on 13th Finance commission and Modernisation of Police Force Scheme (12 crores) | ',' |  | ',' |  | ',' |  | ',' |  | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 13th Finance Commission Scheme Phase II & III | ',' |  | ',' |  | ',' |  | ',' |  | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | Funds received under Annual Plan 2014-15 | ',' |  | ',' |  | ',' |  | ',' |  | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | Funds received under Annual Plan 2015-16 | ',' |  | ',' |  | ',' |  | ',' |  | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | Consturction works of Intelligence Headquarter Building | ',' |  | ',' |  | ',' |  | ',' |  | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | Annual Maintenance of PPHQ Building Works | ',' |  | ',' |  | ',' |  | ',' |  | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | Prisons Deptt. Funds | ',' |  | ',' |  | ',' |  | ',' |  | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | DAV School Ludhiana Works | ',' |  | ',' |  | ',' |  | ',' |  | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | DAV School Sector 48 Works | ',' |  | ',' |  | ',' |  | ',' |  | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | OTHER ACTIVITIES | ',' |  | ',' |  | ',' |  | ',' |  | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | CCTNS Funds | ',' |  | ',' |  | ',' |  | ',' |  | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `projects`(`project_name`, `sanctioned_funds`, `funds_received`, `expenditure`, `funds_available`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | NETS Funds | ',' |  | ',' |  | ',' |  | ',' |  | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');

## Activites Under Project
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at sadar Bathinda | ',' | M/SAranaya Buildcon and Engineers | ',' | ',' | 210.82 | ',' | 18664153.73 | ',' | -13.97% | ',' | 16056771 | ',' | 5 | ',' | 0 | ',' | 01.03.2019 | ',' | 28.02.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H-1 at Bhadaur | ',' | M/S A.J.Builders& contractors | ',' | ',' | 192.09 | ',' | 16872672.3 | ',' | -7.51% | ',' | 18442094 | ',' | 4 | ',' | 0 | ',' | 01.03.2019 | ',' | 28.02.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at Khanouri | ',' | M/S Sai construction CO | ',' | ',' | 215.5 | ',' | 17274087.09 | ',' | -8.99% | ',' | 18684788 | ',' | 10 | ',' | 0 | ',' | 01.03.2019 | ',' | 28.02.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at Jourkian | ',' | M/S Raghu Nath goyal | ',' | ',' | 214.02 | ',' | 19384313.59 | ',' | -7.15% | ',' | 21168847.43 | ',' | 9 | ',' | 0 | ',' | 07.03.2019 | ',' | 06.03.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H atCity Khanna | ',' | M/S A.J.Builders& contractors | ',' | ',' | 207.06 | ',' | 16308199.98 | ',' | -8.51% | ',' | 18693489.2 | ',' | 4 | ',' | 0 | ',' | 07.03.2019 | ',' | 06.03.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H a Maloud distt Khanna | ',' | sh. Jatinder Kumar,Contractor | ',' | ',' | 211.12 | ',' | 17389901.71 | ',' | -7.55% | ',' | 18324448.59 | ',' | 16 | ',' | 0 | ',' | 07.03.2019 | ',' | 06.03.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at shambu Distt Patiala | ',' | M/S Sh. Krishna builders | ',' | ',' | 236.3 | ',' | 15997338.34 | ',' | -8.43% | ',' | 16548400.06 | ',' | 12 | ',' | 0 | ',' | 07.03.2019 | ',' | 06.03.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at Tarsikka,DisttAmritsar | ',' | TheUniversal CO-OP L&C Society Ltd | ',' | ',' | 209.93 | ',' | 15783217 | ',' | -12.76% | ',' | 17064782.45 | ',' | 19 | ',' | 0 | ',' | 07.03.2019 | ',' | 06.03.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at Division No.1, Pathankot | ',' | M/S Bhupinder Singh & Associates | ',' | ',' | 205.86 | ',' | 17359704 | ',' | -5.1% | ',' | 19074501.49 | ',' | 6 | ',' | 0 | ',' | 07.03.2019 | ',' | 06.03.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at Taragarh,Distt Pathankot | ',' | M/S Bhupinder Singh & Associates | ',' | ',' | 186.21 | ',' | 17690221 | ',' | -3.33% | ',' | 19052472.55 | ',' | 6 | ',' | 0 | ',' | 07.03.2019 | ',' | 06.03.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at Sadar Moga | ',' | M/SThakur builders | ',' | ',' | 207.35 | ',' |  | ',' | -5.01% | ',' |  | ',' | 14 | ',' | 0 | ',' | 31.05.2019 | ',' | 30.05.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at City kharar,Distt SASNagar | ',' |  | ',' | ',' | 257.06 | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 0 | ',' |  | ',' |  | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at Zirakpur,Distt SAS Nagar | ',' |  | ',' | ',' | 207.7 | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 0 | ',' |  | ',' |  | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H atBahaw Wala,Distt fazilka | ',' | M/S SatpalContractor | ',' | ',' | 206.43 | ',' |  | ',' | -2.51% | ',' |  | ',' | 11 | ',' | 0 | ',' | 31.05.2019 | ',' | 30.05.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H atLakha Wali,,DisttMukatsar | ',' | The Mohan Ke uttar CO-Op L&Csociety Ltd | ',' | ',' | 209.06 | ',' |  | ',' | -1.79% | ',' |  | ',' | 18 | ',' | 0 | ',' | 31.05.2019 | ',' | 30.05.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at Talwandi Bhai,,DisttFerozepur | ',' | M/S Sohan lalRamesh Kumar | ',' | ',' | 205.92 | ',' |  | ',' | -11.2% | ',' |  | ',' | 13 | ',' | 0 | ',' | 31.05.2019 | ',' | 30.05.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at Rampura sadar,,Distt. Bathinda | ',' | M/S P.K.Bansal& Contractor | ',' | ',' | 207.88 | ',' |  | ',' | -11.5% | ',' |  | ',' | 7 | ',' | 0 | ',' | 31.05.2019 | ',' | 30.05.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at Khem Karan distt Tarn Taran | ',' | The Lango Mahal CO-OP L&C Society Ltd | ',' | ',' | 214.62 | ',' |  | ',' | -16.1% | ',' |  | ',' | 17 | ',' | 0 | ',' | 31.05.2019 | ',' | 30.05.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at Sidhwan Bet | ',' |  | ',' | ',' | 186.46 | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 0 | ',' |  | ',' |  | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at Bilga,Jailandhar | ',' | M/S Pepsu Constn CO | ',' | ',' | 189.24 | ',' |  | ',' | -4.15% | ',' |  | ',' | 8 | ',' | 0 | ',' | 31.05.2019 | ',' | 30.05.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at Basti Bawa Khel,Jalandhar | ',' |  | ',' | ',' | 188.13 | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 0 | ',' |  | ',' |  | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');
INSERT INTO `project_activity`(`project_id`, `activity_name`, `address`, `funds_allocated`, `sanction_amount`, `dnit_amount`, `allotment_below_above`, `allotment_amount`, `contractor_id`, `supervisor_id`, `date_start`, `scheduled_date_completion`, `extension`, `actual_date_completion`, `expenditure_released`, `remarks`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`, `finyear_id`) VALUES (' | 1 | ',' | Construction of Standard Police Station building type-H at Mukanpur,distt SBS Nagar | ',' | Sh. Jatinder Kumar contractor | ',' | ',' | 190.28 | ',' |  | ',' | -4.55% | ',' |  | ',' | 16 | ',' | 0 | ',' | 31.05.2019 | ',' | 30.05.2020 | ',' | ',' | ',' | ',' | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ',' | 1 | ');

## Funds Recd Details
13th finance Commission (Phase I)
Description of Bills | Gross Amount | Net Amount Released | Mode of Payment | Payment released through RTGS / NEFT | Date of Payment | Remarks

## Expenditure Details
EXPENDITURE/ PAYMENT DETAILS : Construction of P.S. Building Type H at Sadar Bathinda
Description of Bills | Gross Amount | Net Amount Payable | Mode of Payment |  |  | Payment released through RTGS / NEFT |  | Amount Released | Date of Payment | Other contigent Payments/ Expenses | Total Expenditure | Remarks
|  |  | RTGS/NEFT |  | Cheque | Name of Bank | Account Number
|  |  | Account No. | IFSC Code

## Scheme Wise Funds
13th finance Commission (Phase I)
Name of the Work | Funds allocated | Technical Sanction Amount | DNIT Amount | Allotment |  | Name of Contractor | Date of Start | Scheduled Date of Completion | Extension if any | Actual Date of completion | Expenditure / Payment released | Remarks
|  |  |  | Below/ Above | Amount

## Details of Contractor
| `department_id |  | name |  | images |  | thumbnail1 |  | thumbnail2 |  | mobile |  | email |  | username |  | password |  | forgot_psw |  | users_type_id |  | activation |  | activation_link |  | tokenid`
INSERT INTO `users_mst`(`department_id`, `name`, `images`, `thumbnail1`, `thumbnail2`, `mobile`, `email`, `username`, `password`, `forgot_psw`, `users_type_id`, `activation`, `activation_link`, `tokenid`) VALUES (' | 1 | ',' | M/S A.J.Builders & contractors | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 5 | ',' | 1 | ',' |  | ',' |  | ');
INSERT INTO `users_mst`(`department_id`, `name`, `images`, `thumbnail1`, `thumbnail2`, `mobile`, `email`, `username`, `password`, `forgot_psw`, `users_type_id`, `activation`, `activation_link`, `tokenid`) VALUES (' | 1 | ',' | M/S Aranaya Buildcon and Engineers | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 5 | ',' | 1 | ',' |  | ',' |  | ');
INSERT INTO `users_mst`(`department_id`, `name`, `images`, `thumbnail1`, `thumbnail2`, `mobile`, `email`, `username`, `password`, `forgot_psw`, `users_type_id`, `activation`, `activation_link`, `tokenid`) VALUES (' | 1 | ',' | M/S Bhupinder Singh & Associates | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 5 | ',' | 1 | ',' |  | ',' |  | ');
INSERT INTO `users_mst`(`department_id`, `name`, `images`, `thumbnail1`, `thumbnail2`, `mobile`, `email`, `username`, `password`, `forgot_psw`, `users_type_id`, `activation`, `activation_link`, `tokenid`) VALUES (' | 1 | ',' | M/S P.K.Bansal& Contractor | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 5 | ',' | 1 | ',' |  | ',' |  | ');
INSERT INTO `users_mst`(`department_id`, `name`, `images`, `thumbnail1`, `thumbnail2`, `mobile`, `email`, `username`, `password`, `forgot_psw`, `users_type_id`, `activation`, `activation_link`, `tokenid`) VALUES (' | 1 | ',' | M/S Pepsu Constn CO | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 5 | ',' | 1 | ',' |  | ',' |  | ');
INSERT INTO `users_mst`(`department_id`, `name`, `images`, `thumbnail1`, `thumbnail2`, `mobile`, `email`, `username`, `password`, `forgot_psw`, `users_type_id`, `activation`, `activation_link`, `tokenid`) VALUES (' | 1 | ',' | M/S Raghu Nath goyal | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 5 | ',' | 1 | ',' |  | ',' |  | ');
INSERT INTO `users_mst`(`department_id`, `name`, `images`, `thumbnail1`, `thumbnail2`, `mobile`, `email`, `username`, `password`, `forgot_psw`, `users_type_id`, `activation`, `activation_link`, `tokenid`) VALUES (' | 1 | ',' | M/S Sai Construction CO | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 5 | ',' | 1 | ',' |  | ',' |  | ');
INSERT INTO `users_mst`(`department_id`, `name`, `images`, `thumbnail1`, `thumbnail2`, `mobile`, `email`, `username`, `password`, `forgot_psw`, `users_type_id`, `activation`, `activation_link`, `tokenid`) VALUES (' | 1 | ',' | M/S Satpal Contractor | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 5 | ',' | 1 | ',' |  | ',' |  | ');
INSERT INTO `users_mst`(`department_id`, `name`, `images`, `thumbnail1`, `thumbnail2`, `mobile`, `email`, `username`, `password`, `forgot_psw`, `users_type_id`, `activation`, `activation_link`, `tokenid`) VALUES (' | 1 | ',' | M/S Shri Krishna Builders | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 5 | ',' | 1 | ',' |  | ',' |  | ');
INSERT INTO `users_mst`(`department_id`, `name`, `images`, `thumbnail1`, `thumbnail2`, `mobile`, `email`, `username`, `password`, `forgot_psw`, `users_type_id`, `activation`, `activation_link`, `tokenid`) VALUES (' | 1 | ',' | M/S Sohan Lal Ramesh Kumar | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 5 | ',' | 1 | ',' |  | ',' |  | ');
INSERT INTO `users_mst`(`department_id`, `name`, `images`, `thumbnail1`, `thumbnail2`, `mobile`, `email`, `username`, `password`, `forgot_psw`, `users_type_id`, `activation`, `activation_link`, `tokenid`) VALUES (' | 1 | ',' | M/S Thakur builders | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 5 | ',' | 1 | ',' |  | ',' |  | ');
INSERT INTO `users_mst`(`department_id`, `name`, `images`, `thumbnail1`, `thumbnail2`, `mobile`, `email`, `username`, `password`, `forgot_psw`, `users_type_id`, `activation`, `activation_link`, `tokenid`) VALUES (' | 1 | ',' | Raghu Nath Goyal | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 5 | ',' | 1 | ',' |  | ',' |  | ');
INSERT INTO `users_mst`(`department_id`, `name`, `images`, `thumbnail1`, `thumbnail2`, `mobile`, `email`, `username`, `password`, `forgot_psw`, `users_type_id`, `activation`, `activation_link`, `tokenid`) VALUES (' | 1 | ',' | Shri Jatinder Kumar, Contractors | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 5 | ',' | 1 | ',' |  | ',' |  | ');
INSERT INTO `users_mst`(`department_id`, `name`, `images`, `thumbnail1`, `thumbnail2`, `mobile`, `email`, `username`, `password`, `forgot_psw`, `users_type_id`, `activation`, `activation_link`, `tokenid`) VALUES (' | 1 | ',' | The Lango Mahal CO-OP L&C Society Ltd | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 5 | ',' | 1 | ',' |  | ',' |  | ');
INSERT INTO `users_mst`(`department_id`, `name`, `images`, `thumbnail1`, `thumbnail2`, `mobile`, `email`, `username`, `password`, `forgot_psw`, `users_type_id`, `activation`, `activation_link`, `tokenid`) VALUES (' | 1 | ',' | The Mohan Ke uttar CO-Op L&Csociety Ltd | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 5 | ',' | 1 | ',' |  | ',' |  | ');
INSERT INTO `users_mst`(`department_id`, `name`, `images`, `thumbnail1`, `thumbnail2`, `mobile`, `email`, `username`, `password`, `forgot_psw`, `users_type_id`, `activation`, `activation_link`, `tokenid`) VALUES (' | 1 | ',' | The Universal Co-op L&C Society Ltd. | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' |  | ',' | 5 | ',' | 1 | ',' |  | ',' |  | ');

## Sheet1
INSERT INTO `contractor`(`users_id`, `firm_name`, `address`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`) VALUES (' | 4 | ',' | M/S A.J.Builders & contractors | ',' | House No. 14-+OB/334, Arya Samaj Block, Dhuri District Sangrur | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ');
INSERT INTO `contractor`(`users_id`, `firm_name`, `address`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`) VALUES (' | 5 | ',' | M/S Aranaya Buildcon and Engineers | ',' | H.No. 221, Kuh Wali Gali, Jawahar Nagar, Goniana Mandi, District Bathinda | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ');
INSERT INTO `contractor`(`users_id`, `firm_name`, `address`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`) VALUES (' | 6 | ',' | M/S Bhupinder Singh & Associates | ',' | GT Road Batala | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ');
INSERT INTO `contractor`(`users_id`, `firm_name`, `address`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`) VALUES (' | 7 | ',' | M/S P.K.Bansal& Contractor | ',' |  | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ');
INSERT INTO `contractor`(`users_id`, `firm_name`, `address`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`) VALUES (' | 8 | ',' | M/S Pepsu Constn CO | ',' |  | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ');
INSERT INTO `contractor`(`users_id`, `firm_name`, `address`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`) VALUES (' | 9 | ',' | M/S Raghu Nath goyal | ',' |  | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ');
INSERT INTO `contractor`(`users_id`, `firm_name`, `address`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`) VALUES (' | 10 | ',' | M/S Sai Construction CO | ',' | Hno. 27-A, Sector 18, Guru gian Vihar, Jawaddi, Ludhiana | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ');
INSERT INTO `contractor`(`users_id`, `firm_name`, `address`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`) VALUES (' | 11 | ',' | M/S Satpal Contractor | ',' |  | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ');
INSERT INTO `contractor`(`users_id`, `firm_name`, `address`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`) VALUES (' | 12 | ',' | M/S Shri Krishna Builders | ',' | House No. 5545, Sector 38, West, Chandigarh | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ');
INSERT INTO `contractor`(`users_id`, `firm_name`, `address`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`) VALUES (' | 13 | ',' | M/S Sohan Lal Ramesh Kumar | ',' |  | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ');
INSERT INTO `contractor`(`users_id`, `firm_name`, `address`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`) VALUES (' | 14 | ',' | M/S Thakur builders | ',' |  | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ');
INSERT INTO `contractor`(`users_id`, `firm_name`, `address`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`) VALUES (' | 15 | ',' | Raghu Nath Goyal | ',' | # 286, Vishal Nagar, Phase II, Bathinda | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ');
INSERT INTO `contractor`(`users_id`, `firm_name`, `address`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`) VALUES (' | 16 | ',' | Shri Jatinder Kumar, Contractors | ',' | 61-B, Rose Enclave, Pakhowal, Ludhiana | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ');
INSERT INTO `contractor`(`users_id`, `firm_name`, `address`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`) VALUES (' | 17 | ',' | The Lango Mahal CO-OP L&C Society Ltd | ',' |  | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ');
INSERT INTO `contractor`(`users_id`, `firm_name`, `address`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`) VALUES (' | 18 | ',' | The Mohan Ke uttar CO-Op L&Csociety Ltd | ',' |  | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ');
INSERT INTO `contractor`(`users_id`, `firm_name`, `address`, `status_id`, `status_date`, `status_remarks`, `is_cancel`, `cancel_date`, `cancel_reason`) VALUES (' | 19 | ',' | The Universal Co-op L&C Society Ltd. | ',' | Hno. 8861, St. No. 5/6 Kot Baba Deep Singh, Amritsar | ',' | Pending | ',' | ',' | ',' | No | ',' | ',' | ');